## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | (Fill your Project Number here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Status
PROJECT NUMBER | 2
PROJECT NAME | Social Media Content Automation
PROJECT MENTOR (sponsor) | Meera Rajagopalan
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | TA | 1 | 1 | Done |  | 0 | 0
GIT Repository setup | Preparation | Samarth | 0.3 | 0.3 | Done |  | 0 | 0
Client meeting | Coordination | TA | 1 | 1 | Done | Make sure scoping questions are included | 0 | 0
Get account and configure website | Preparation | Vidhi | 3 |  | Planned | Website will be included in later half of the project
Research existing technology | Preparation | All members | 10 to 15 |  | Ongoing | Exploring all the new tech that can be used
Project synopsis writeup | Documentation | Samarth | 1 | 1 | Done |  | 0 | 0
Identify role owners | Preparation | All members | 1 |  | Ongoing | Multiple roles are OK - think about role & reponsibility distribution
Team Meeting | Coordination | All members | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Samarth | 1 |  | Ongoing
Week 2 (January 22 - January 28)
Learn Eclipse | Preparation | NA |  |  | Planned | NA in our project
GIT Repository setup | Preparation | Samarth | 0.5 | 0.5 | Done | Updated with project synopsis and scope | 0 | 0
Discuss bug report software | Preparation | All members | 2024-02-03 |  | Planned | This is critical to project success
Develop questions for requirements elicitation | Documentation | All members | 5 |  | Ongoing | Make sure scoping questions are included
Get account and configure website | Preparation | NA |  |  | Planned
Team Meeting | Coordination | All members | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Samarth | 0.5 | 0.5 | Done |  | 0 | 0
Weekly Notion page updation | Documentation | Anna | 0.5 | 0.5 | Done |  | 0 | 0
Week 3 (January 29 - February 4)
Meet with Client | Requirements | All members | 1 | 1 | Done |  | 0 | 0
Research on API calls | Preparation | Kuvam | 3 to 4 |  | Ongoing
Automation on Instagram | Development | Samarth | 4 to 6 |  | Ongoing
Automation on Facebook | Development | Kuvam | 3 to 5 |  | Ongoing
Webscrapping data from client's website | Development | Kuvam,Vidhi | 1 to 2 | 1.5 | Done
Weekly Notion page updation | Documentation | Anna | 0.5 | 0.5 | Done
Week 4
Week 5
Week 6
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically